## Slide 1: DanceCity Revolution
By Michael Hong and Garry Fong

## Slide 2: Introduction
Our group members are Michael and Garry
Our project was Dance City Revolution, centered around teaching kids the joy of dance, and improving their fitness levels
Our project was held over 4 sessions, and our audience was the Selkirk and Secord OOSC programs
We had no clear-cut primary objective, but we did achieve our secondary objective, which was having the kids learn a choreography of a style of their choosing

## Slide 3: Process
Activities were performed as planned except for sessions 1 and 3
Our project reached its intended target population of 16
The participants weren’t interested at first, but as the sessions continued on, they began to grow an interest into what they were doing
The planning and activities would have gone more smoothly if more communication was involved, particularly for session 3

## Slide 4: Outcomes
Our primary goals in this project were to
Increase fitness of our target age group (achieved)
Increase interest in dance of our target age group (achieved)
Our secondary goal in this project was to
Have the kids learn a choreography from a style of dance of their choosing (achieved)
The participants experienced an improvement in attitude towards the program and dance as they learned more of the choreography. They also increased in skill in dance.
We had expected the participants to improve in fitness in attitude, these were realistic expectations, and they were met.
The effects of the project on partnering with CCNH was mostly felt in terms of resources, for example, we never would’ve obtained permission to use the venue we ended up using if not for the backing of CCNH. The effects of this project on CCNH are, as stated previously in regards to the community, an improvement in fitness and attitude for children.
Short-term, the kids will hopefully know a dance choreography. Long term, the kids will hopefully have increased fitness, obtain an interest in dance, and experience an improvement in general mood.

## Slide 5: Lessons learned
Through this project, we learned how to
organize and execute a session plan within a timeframe
maintain interest of participants
plan for emergencies as needed (on the spot)
communicate effectively between leaders

## Slide 6: Self Evaluation
Throughout this project, we had highs and lows. In the end, we learned from most of our mistakes and our final session was wildly successful, due to both our increase in ability and regaining the usage of our volunteers. Overall, we’d rate ourselves as successful, seeing as how we achieved all of our goals (Have the kids have fun, move around, and learn the dance) despite having many problems that we needed to overcome.

## Slide 7: Future Roles at CCNH
In the future, we see ourselves continuing to be involved in the Neighbourhood House as volunteers, using the knowledge we gained in this Summer Youth Project to benefit our work.